On wiki2tei ... i have done a couple of transformations : it was fairly painful, though no more so than translating gutenberg xhtml. in both cases, you need to remember to run the HTML through something like tidy to make sure that it's in unicode, and that the empty tags get properly indicated. Also possibly to convert named character ewntities like &nbsp; to their numeric equivalents. Then it's a matter of writing xslt to get rid of the (hugely redundant) tagging that wikisource puts in. Attached is the stylesheet I used to convert the wikisource text of an obscure victorian novel ...

Annotating European Novels (1840-1920) for Distant Reading
A Critical Assessment of Tools
Time table
1. Set up different repository (Lou; deadline: tomorrow)
2. 20+ novels in ELTeC level 0 (deadline: 15th November 2018):
  1. Certain / minimum:
    1. English (Lou)
    2. Hungarian (DONE)
    3. Slovenian (Marco)
    4. Italian (Fabio)
    5. French (Serge + Christof)
    6. German (Fotis)
    7. Portuguese (Diana)
  2. Possible:
    1. Spanish ()
    2. Norwegian ()

1. Select sample (responsible: Lou; deadline: 22 November 2018):
  1. 5 random passages of 400 “tokens” from each text: 100 samples per language. Whitespace tokenizer: 2,000 whitespace-delimited tokens per text.
    1. Tokens that don’t fit a entire sentence get trimmed manually.
    2. Exclude headings, include poetry
  2. Make available
2. Groups: apply (presumably) the best tool that they have and return the output (29 November 2018)
3. Annotators correct the annotation (deadline: 11 january 2019)
4. Corrections go back to the groups and they do their thing: perform comparison of tools (for each language); error analysis; suggestions for improvement and finetuning; comparison to baseline figures for “normal”, contemporary text (9 March 2019). Write-up in Google Doc
5. Write up (12 April 2019)

Potential venues [to be decided]
Language Resources and Evaluation / LREC
Latech / CLFL
Journal of Quantitative Linguistics
Journal of AI Research / AI Review
Digital Scholarship in the Humanities
New Springer journal on DH (International journal of Digital Humanities)
DHQ
Take account review time, and the literary orientation also
Introduction
- What is annotation (in the context of this paper)?
- Why do we need the annotations for distant reading? What is the added value with respect to raw text?
- Short description of the COST project (what is the European novel?)
- Which tools:
  - Open-source

Languages (50 novels that can reach level-0 within the month):
1. English
2. Hungarian
3. Slovenian
4. Italian
5. French
6. German
7. (Spanish)
8. (Portuguese)
9. ...

Evaluation data:
E.g. 10 random passages of 100 sentences, ca. 1000 words

Data
- Discuss corpus (6 languages in first iteration of ELTeC corpus):
  - Composition (Metadata)
  - Source of texts (with justification)
  - Mark-up
- Challenges of the data:
  - Historic (variability in orthography, diachronic shifts in vocabulary)
  - Multilinguality
  - Corpus composition; cultural biases might be an issue; cf. selection criteria:
    - gender balance
    - language balance
    - diachronic balance
    - genre balance
    - representativeness and endurance
  - Lack of resources in general: data size, data quality (e.g. OCR), …
  - Consistency (WHERE ARE THE PAGE BREAKS???)
- Methodological issue: how is the pre-existing mark-up maintained? Which elements/layers are preserved?

Task: problem statement
Apply off-the-shelf annotation tools to our materials

Subtasks
1. Cluster:
  1. Sentence splitting
  2. Tokenization
2. Cluster:
  1. Part of Speech tagging (head tags) -> Noun
  2. Morphological analysis -> Case
  3. Lemmatisation (what about MWU?)
3. (Named) entity recognition
4. Direct speech detection
5. Sentiment analysis

Language	Sentence / Tokenisation / Direct Speech	POS / Morph / Lemma	Named Entity Recognition	Sentiment Analysis
English (Lou)	Mike	Silvie	Ranka
Hungarian	ELTE.DH	ELTE.DH	ELTE.DH	ELTE.DH
Slovenian (Marco)
Italian (Fabio)
French (Serge + Christof)	Serge	Silvie, Ioana	Ioana
German (Fotis)	Fotis	Fotis, Silvie	Fotis
Portuguese (Diana)	Diana	Diana	Diana	Diana

For each task
1. Task definition
2. State of the art
3. Suitable evaluation metrics
4. Uniform labeling system
5. Common tools
6. Baseline results (for non-literary modern newspaper-like text)
7. Annotation standard proposal for test data
8. Performance off-the-self on 19c novel data